## RR Checklist
RENTAL REHABILITATION INITIATIVE - PROJECT CHECKLIST
The following list of file documentation MEDC expects all grantees to maintain in their local project files. The list of required documents is generally organized in chronological order and broken into key phases in the lifecycle of a specific project.
| COLUMN B IA = If Applicable R = Required S = Suggested |  | COLUMN C CDM = Commuity Development Manager ER = Environmental Review G = Grantee provides GAM = Grant Administration Manual PS = CDBG Program Specialist
DATE |  |  | STEP 1 ¦ APPLICATION Application and required attachments submitted to MEDC.
| R | CDM | 1. Application
| R | CDM | 2. Required Attachments
| R | CDM or G | 3. Before Photos Exterior of building (all sides) and interior of each proposed rental units or vacant space.
STEP 2 ¦ LETTER OF INTENT MEDC provides LOI approving project.
| IA | G | 1. Certified Grant Administrator (CGA) If UGLG decides to use a CGA, see GAM 14 for guidance.
| IA | G | 1a. Request for Proposals Certified Grant Administrative Services
| IA | 14-A | 1b. Procurement Process for Selection of a Certified Grant Administrator
| R | PS | 2. Compliance Checklist Grantee submits required documents.
STEP 3 ¦ APPLICANT ELIGIBILITY Confirm eligibility of property owner.
| R | G | 1. Property Tax Verification Verification that property taxes have been paid to date.
| R | G | 2. Property Insurance Obtain proof of property insurance.
| R | G | 3. Recorded Warranty Deed, Land Contact and LC Verification, OR Title Insurance MEDC expects grantees to trace the current owner’s title back to a recorded warranty deed, and any land contracts must be recorded. If the ownership of the property cannot be clearly traced to a warranty deed, the grantee should obtain a title insurance policy covering its lien on the property.
| IA | 2-H | 4. Land Contract Subordination Required by Property Owner when assisted property is being purchased by a land contract.
5. Applicant Receipt of following documents:
| IA | 2-I | 5a. Lead Paint - Renovate Right, EPA-740-F-08-002, 03.08 Lead documents are required when the home is built prior to 1978.
| R | 2-J | 5b. Fair Housing: Equal Opportunity for All, HUD-1686-FHEO, 09.08
| IA | 5-S | 6. Lead-Based Paint Applicability and Compliance Worksheet
| IA | 5-V | 7. Asbestos Applicability Worksheet
STEP 4 ¦ PROPERTY COMPLIANCE Grantee must complete a variety of inspections to evaluate the scope of necessary activity and estimate costs.
| R | 5-P | 1. Environmental Review (ER) Process Flowchart Complete the flowchart to determine level of ER required.
| R | GAM 5 | 2. Environmental Review documents Based on ER level, complete ER.
| R | 5-S | 3. Lead-Based Paint Applicability and Compliance Worksheet
| IA | G | 4. Lead Risk Assessment and Inspection Will be provided by Lead Risk Assessor
| IA | 2-K | 5. Occupant Protection Plan, DCH-1109 Required for rehabilitation activities undergoing lead paint remediation activities with tenants/occupants. NA for structures built post-1978. NA if lead is remediated before occupancy.
| IA | G | 6. Asbestos Testing Required if asbestos is found.
| R | 4-B | 7. Bid and Contract Document SAMPLE
| IA | GAM 10 | 8. Davis Bacon Required if 8 or more units
| S | ER | 9. Transaction Screening For 1-4 units in a downtown mixed-use building (2nd or 3rd floor residential only), a Transaction Screening is required. For 5 or more units in a mixed-use building, a Transaction Screening is not an option as a Phase I ESA is required.
| IA | ER | 10. Phase I Environmental Site Assessment For 1-4 units, if Transaction Screening identifies RECs, then Phase I ESA is required and needs CDD approval. For 5 or more units in a mixed-use building, Phase I ESA is required.
| IA | ER | 11. Phase II Environmental Site Assessment Determined by Phase I ESA.
STEP 5 ¦ GRANT AGREEMENT ER and Compliance Checklist are complete and submitted to CDBG Specialist.
| R | CDM | 1. Term Sheet CDM will email term sheet for Building Owner and UGLG signatures/dates.
| R | PS | 2. Grant Agreement Specialist will email grant agreement for UGLG signatures/dates.
| R | G | 3. Payment Requests Due monthly at a minimum or at least each quarter. Submit 8-A1, 8-A2 and supporting documentation. If Davis Bacon, submit 10-K, 10-L and supporting documentation.
STEP 6 ¦ BIDDING AND CONTRACTOR SELECTION After determining a project’s initial feasibility, a contractor can be identified, and actual costs of the project can be determined.
| R | G | 1. Cost Estimates provided by architect OR prepared Bid Package provided by UGLG.
| IA | G | 2. Bonding and Insurance Required for CDBG projects over $250,000.
| IA | G | 2. List of Contractors Invited to Bid, if UGLG providing contractor
| IA | G | 3. Copies of Bids Received
| IA | G | 4. Bid Comparison Summary and Selected Contractor, if UGLG providing contractor
| R | G | 5. Verification That Selected Contractor(s) is Not on Debarred List DUNS number look up at http://mycredit.dnb.com/search-for-duns-number/ Enter company name, city and state. Click Search. DUNS number will be emailed to you.
Go to SAM at https://www.sam.gov/portal/public/SAM/ Enter UEI number, click search. Look for status at left of company name (Exclusion). Click View Details for more info. Print results and place in file.
| R | G | 6. Limited Denial of Participation, HUD Funding Disqualifications and Voluntary Abstentions https://www5.hud.gov/ecpcis/main/ECPCIS_List.jsp Print results of search from above website and place in file.
| R | G | 7. Validation of Contractor License https://www2.dleg.state.mi.us/colaLicVerify/ Licenses must be verified to ensure they have not been revoked, suspended or lapsed. Print results of search from above website and place in file.
STEP 7 ¦ PROJECT AGREEMENTS
| R | G | 1. Escrow Agreement
| IA | G | 2. Development Agreement
| R | G | 3. Escrowed Match Funds verification
STEP 8 ¦ CONSTRUCTION MANAGEMENT
| R | G | 1. Contractor(s) License
| R | G | 2. Contractor(s) Insurance
| IA | G | 3. Contractor(s) Lead Training Certification Required for lead abatement.
| R | 4-B | 4. Bid and Contract Document SAMPLE
| R | 4-R | 5. DBRA Packet A required attachment to the Construction Contract
| IA | 9-B1 | 6. Section 3 Plan for General Contractor Compliance requirements of Section 3 of the HUD Act of 1968 are triggered when a recipient receives a grant award in excess of $200,000.
| IA | 9-B2 | 7. Section 3 Plan for Subcontractors
| IA | G | 8. Change Order(s)
| R | G | 9. Local Building Official's Inspection Report Provided by local building official if permit required.
| R | G | 10. Sworn Statements
| R | G | 11. Partial and Final Unconditional Lien Waiver(s)
| IA | G | 12. Lead Clearance Test Results
| IA | G | 13. Lead Based Paint Abatement
| IA | G | 14. Asbestos Abatement
| R | G | 15. Occupancy Report
| R | 4-P | 16. Contract and Subcontract Activity Due annually for period 10/1 to 9/30, completed by contractor, submit to Specialist, see GAM Chapter 10.
| R | 9-C | 17. Section 3 Summary Report Due annually for period 7/1 to 6/30, see GAM Chapter 9
| R | G | 18. After Photos
STEP 9 ¦ TENANT ELIGIBILITY (for newly constructed vacant units)
| R | 2-E | 1. RR Tenant Application For each tenant household, new units, market and affordable rents.
| R | G | 2. Income Verification of Tenants (new units) Use Federal income tax returns for all persons 18 and over. All tax forms must be signed and dated. Enter data into HUD Income Eligibility Calculator to confirm income eligibility at https://www.hudexchange.info/incomecalculator/
| R | G | 3. Lease for Tenants (new units)
| R | G | 3a. Fair Market Rent. Provide copy of the applicable fair market rent table with the lease for each LMI tenant.
4. Tenant Receipt of following documents:
| IA | 5-R | 4a. Disclosure of Information Lead-Based Paint and.or Lead-Based Paint Hazards
| R | 2-M | 4b. Fair Housing Signature Receipt
| R | GAM | 5. Utility Allowance Schedule. Use MSHDA utility allowance schedule for utilities being paid by tenant. Provide a copy of the form with the lease for each low mod tenant.
STEP 10 ¦ PROJECT CLOSEOUT AND MONITORING Rental projects carry specific ongoing responsibilities for the grantee. Grantees are required to document ongoing compliance with the tenant rent affordability and property standards required by of rental projects throughout the applicable affordability period (5 years).
| R | PS | 1. Monitoring Onsite monitoring of the units and UGLG internal processes will occur upon selection of LMI tenants.
| R | 2-L | 2. RR Annual Affordability Report Submit to Program Specialist by December 31 of each year for 5 years.
| S | G | 3. Annual Inspection of units
| S | G | 4. Pre-Warranty Expiration Follow-up for Warranty Repairs It may be a good idea to follow-up six months before the warranty on workmanship and materials expires. While the contractor provides the warranty, buyers will often initially come to the grantee with problems, and it’s best to be proactive about identifying problems before the warranty runs out.