## Sheet1
BCVision 2017 Timeline |  | February/March | April | May | June | July | August | September | October | November | December | January
National Equity Project | Racial Equity | Racial Equity Commitment Statement | bar: April to August
Core Team Support and Collaboration | bar: April to August
Educational Equity | bar: April to August
Advisory Team | bar: April to August
Steering Committee | bar: April to August
Aligned Racial Equity Efforts | bar: April to August
Community Engagement | bar: April to August
Executive Leadership Coaching | bar: April to August
Public Policy Associates | Data | Dashboard Development | bar: April to August
Support Action Teams
Primary Data Collection/Management
Community Change Model and Impact
BCPulse & Great Start Collaborative | KR | Enquirer Guest Columns | bar: April to June
Campaigns - Fill Slots & Raise Funds
Leader Training as Ambassadors
Fund Raising Campaign
Employers Promote Enrollement w/ Employees
Launch of Shared Services Alliance
Partnership Between CISD & DHHS to Connect Families
Shared Website Launch
Billboard Campaign
Shared Services on the Web
BCVision | CCR/KR | Community in Schools Presentation
Community in Schools Taskforce
BCVision | CCR | Rollout of Study
Race Conversation
Determine Pipeline Gaps
School Boards Joint Meeting
Develop Career Pipeline
Partnership with BC CAN
Develop Metrics
Community in Schools Kickoff
Weber Shandwick | Communications | Toolkit
Website-Phase II
Equity Commitment Messaging
JumpStart
Co-Chair Training
Education Study Messaging
Leading for Equity Institute
Content Creation/Updates
Social Media Ramp Up
Steering Committee Paid Ads
United Way of Battle Creek & Kalamazoo Region | Community Engagement | Orientations
Engagement with Existing Orgs | bar: April to May
Relationship Building with New Populations | bar: April to May
Events & Informal Outreach | bar: April to May
Chamber of Commerce Eye Opener
Mexican Consulate
Engagement Orientations | bar: April to May
Quarterly Engagement Round Table
Sharing of Ongoing Learning | bar: April to May
Chin National Day
VOCES C/E Dinner
BC Vision Support | bar: April to May
NPC C/E Tols and Resources 5/15
Cereal Festival
VOCES Family Day
Juneteenth
City of Battle Creek | Culture of Vitality | Ensure Work is not Lost
Determine Direction
Ideas from Action Teams
Finalize Plan and Move Forward
Battle Creek Unlimited | Large Business | Data Survey for Employers
Identify Barriers to Employment
Collaboration for Action Plan to Address Top Barriers
$60 million Investment
1,000 new jobs (333 per year)
Battle Creek Chamber, City of Battle Creek, Generation E, & Miller Foundation | Small Business | Secure Mentors
Inventory Existing Data & Identify Gaps
Renwed Approach to Grow Internship Program
Identify 5 Intership Opportunities in Spring
Promotion and Awareness
Develop Format for Mentoring Program
Set Dates for Pitch and Partner Event
Outreach to Partners for Mentors
Identify and Gather Resources
Identify and Develop 5 Summer Internships
Pitch and Partner Event
Pair Mentors/Mentees
Assemble and Cross Reference Data
Checkpoints for Business Advancements
Mentor/Mentee Meetings Completion
Assist w/ Succession Planning
Event for Reporting Growth
10 Fall Internships
Assessment and Evaluation
New Group Rec
Assemble Core EDA
Research CRM Best Practices
Develop Funding and Management Plan for SRM Software
Determine Desired Outputs
Determine Desired Inputs
Purchase and Implement CRM
Beginning Planning for Second Mentor Program
EDA Conduct/Log Retention & Attraction Visists
Design and Production
Identify Data Sources
Workshops/Evaluations/Continuation
Launch Business Portal
Complete 1000 RV/AV
MIWorks! & United Way of Battle Creek & Kalamazoo Region | Workforce Development | Plan 3 Days of Consecutive Opportunnity Fairs Leading Up to Job Fair
Planning for Opportunity Fairs
Business Engagement
Ongoing Transportation Taskforce
Opportunity Fair
Career Pathways Partnership
Planning for Opportunity Fair
3 Days of Consecutive Opportunity Fair
BCVision | Transportation Taskforce |  | April: Conduct Survey/Focus Groups with Stakeholders
Utilize Data
Develop Action Plan