## Table 1
2022 MASTER PLAN - CHECKLIST FOR ACTION
Goal 1: Develop strong and stable neighborhoods that are desirable and have a unique sense of place.
STATUS
Strategy 1.1.1 - Prioritize redevelopment areas
Identify areas within the City that already contain development the community desires and concentrate resources to capitalize on surrounding developments: | 1.1.1 | 1 | PZ, ED, DDA, LB, RDC | GF | Complete
Assemble and develop shovel ready sites in these areas | 1.1.1 | 2 | PZ, ED, LB, PS | GF | Complete
Focus efforts in areas that serve as gateways into the community | 1.1.1 | 2 | PZ, ED, LB, PS | GF, G, F | Complete
Continue with central core developments and riverfront enhancements (See 1.1.5 below) | 1.1.1 | 3 | PZ, ED, DDA LB, PS, RDC | GF, G, F | In Process
Identify areas in the City that are underdeveloped and most feasible for new development: | 1.1.1 | 1 | PZ, ED, LB, PS | GF, G | In Process
Assemble and develop shovel ready sites in these areas | 1.1.1 | 2 | PZ, ED, LB, PS | GF, G | In Process
Work with neighborhood leaders to determine infill opportunities specific to their neighborhood | 1.1.1 | 2 | PZ, ED, LB, PS | GF, G | In Process
Strategy 1.1.2 - Develop a zoning plan that relates to Future Land Use categories
Formulate future development goals through collaboration with representative groups in areas identified in the future land use map | 1.1.2 | 1 | PZ, ED | GF, Other | In Process
Conduct a block-by-block analysis within the defined area to determine appropriate future land use and zoning plan. | 1.1.2 | 3 | PZ, ED | GF, Other | In Process
Based upon input from the representative group’s vision, formulate zoning classifications and standards that would define and support the vision. | 1.1.2 | 3 | PZ, ED | GF, Other | In Process
Strategy 1.1.3 - Revise the zoning ordinance to allow reuse of vacant and abandoned property
Identify vacant and abandoned property areas that no longer fit the zoning classification they are in, or, areas included in the future land use map under a zoning classification that is undefined in the current zoning, and formulate future development goals through collaboration with representative groups | 1.1.3 | 1 | PZ, ED | GF, G | In Process
Based upon input from the representative group’s vision, formulate zoning classifications and standards that would define and support the vision | 1.1.3 | 3 | PZ, ED | GF, G | In Process
Key:
Timeframe - 1: Within a year, 2: 1 to 3 years, 3: More than 3 years, Ongoing: As available/Continuing project
Responsibility - CC: City Council, PZ: Planning & Zoning, ED: Economic Development Division, DDA: Downtown Development Authority, PS: Public Services, Parks: Technical Services, LB: Saginaw County Land Bank, BRA: Brownfield Redevelopment Authority, SHC: Saginaw Housing Commission, R: Riverfront Development Commission, MDOT - Michigan Department of Transportation
Funding - GF: General Fund, Grant: Grants, F: Area Foundations, Other: State and Federal Agencies
Tasks | Strategy | Timeframe | Responsibility | Funding | STATUS
Strategy 1.1.4 - Revise zoning ordinance to provide for a range of appropriate building and construction forms
Update the zoning ordinance to align with the goals and zoning recommendations from the master plan | 1.1.4 | 3 | PZ, ED | GF, G | In Process
Consider a complete rewrite of the zoning ordinance | 1.1.4 | 3 | PZ, ED | GF, G | In Process
Evaluate and streamline requirements and regulate for the kind of development that is truly desired | 1.1.4 | 3 | PZ, ED | GF, G
Make the ordinance and zoning map accessible online | 1.1.4 | 3 | PZ, ED | GF, G | In Process
Ensure the ordinance portrays clear definitions and requirements | 1.1.4 | 3 | PZ, ED | GF, G | In Process
Include easily understood graphics, tables or charts in the zoning ordinance | 1.1.4 | 3 | PZ, ED | GF, G | In Process
Consider expanding Form Based Zoning Code as part of the proposed zoning ordinance rewrite | 1.1.4 | 3 | PZ, ED | GF, G | In Process
Strategy 1.1.5 - Enhance the Riverfront attractiveness through place making
Connect the waterfront to Downtown and Old Town | 1.1.5 | 3 | PZ, ED, DDA, RDC, PS
Identify traffic generators along key corridors, nodes and existing developments within 1,500 ft of the river and each other | 1.1.5 | 3 | PZ, ED, DDA, RDC, PS |  | In Process
Preserve water views and community character | 1.1.5 | 3 | PZ, ED, DDA, RDC, PS |  | On Going
Create streets that are comfortable for pedestrians | 1.1.5 | 3 | PZ, ED, DDA, RDC, PS |  | On Going
Develop an action plan for improvements to the identified pedestrian routes within the Riverfront area | 1.1.5 | 1 | PZ, ED, DDA, RDC, PS |  | In Process
Non-motorized pathways | 1.1.5 |  |  |  | In Process
Identification signage | 1.1.5
Lighting | 1.1.5
Benches | 1.1.5
Key:
Timeframe - 1: Within a year, 2: 1 to 3 years, 3: More than 3 years, Ongoing: As available/Continuing project
Responsibility - CC: City Council, PZ: Planning & Zoning, ED: Economic Development Division, DDA: Downtown Development Authority, PS: Public Services, Parks: Technical Services, LB: Saginaw County Land Bank, BRA: Brownfield Redevelopment Authority, SHC: Saginaw Housing Commission, R: Riverfront Development Commission, MDOT - Michigan Department of Transportation
Funding - GF: General Fund, Grant: Grants, F: Area Foundations, Other: State and Federal Agencies
Tasks | Strategy | Timeframe | Responsibility | Funding | STATUS
Strategy 1.2.1 - Provide quality infrastructure, public services, and public safety to sustain strong neighborhoods
Prioritize capital improvement plans that focus on multimodal transportation systems that accommodate walkers, bikers, bus and rail passengers, and drivers | 1.2.1 | 2 | PZ, ED, PS, MDOT | GF, G, F | On Going
Evaluate and refine the road diet suggestions identified in the Transportation Plan and prioritize these routes for development | 1.2.1 | 3 | PZ, ED, PS, MDOT | GF, G, Other | On Going
Implement the prioritized road diet routes as a way to increase safety and add additional features to the current roadway such as bicycle lanes | 1.2.1 | 3 | PZ, ED, PS, MDOT | GF, G, Other | On Going
Create streets that are comfortable for pedestrians | 1.2.1 | Ongoing | PZ, ED, PS, MDOT | GF, G, Other | On Going
Develop an action plan for improvements to the identified pedestrian routes within the Riverfront area | 1.2.1 | 2 | PZ, ED, PS, DDA, RDC | GF, G, Other | In Process
Strategy 1.2.2 - Ramp up housing renovation, infill construction, and development
Work with neighborhood groups to identify areas for potential infill opportunities | 1.2.2 | 3 | PZ, ED | GF, G, SHC | In Process
Identify appropriate locations for senior-specific and “Missing Middle” housing types within the City of Saginaw | 1.2.2 | 3 | PZ, ED, SHC | GF, G, SHC | In Process
Update zoning ordinance to allow for the following types of building forms where appropriate: | 1.2.2 | 3 | PZ, ED | GF, G | In Process
Accessory dwelling units (ADU) | 1.2.2
Townhouses/rowhouses | 1.2.2
Triplexes | 1.2.2
Quadplexes | 1.2.2
6-plexes | 1.2.2
Stacked flats | 1.2.2
Residential above commercial | 1.2.2
Micro units | 1.2.2
Tiny houses | 1.2.2
Key:
Timeframe - 1: Within a year, 2: 1 to 3 years, 3: More than 3 years, Ongoing: As available/Continuing project
Responsibility - CC: City Council, PZ: Planning & Zoning, ED: Economic Development Division, DDA: Downtown Development Authority, PS: Public Services, Parks: Technical Services, LB: Saginaw County Land Bank, BRA: Brownfield Redevelopment Authority, SHC: Saginaw Housing Commission, R: Riverfront Development Commission, MDOT - Michigan Department of Transportation
Funding - GF: General Fund, Grant: Grants, F: Area Foundations, Other: State and Federal Agencies
Tasks | Strategy | Timeframe | Responsibility | Funding | STATUS
Strategy 1.2.3 - Update the zoning ordinance to include flexible zoning techniques
Adopt zoning classifications that will shape inviting, walkable, vibrant communities, rather than inhibit them | 1.2.3 | 3 | PZ, ED | GF, G | In Process
Revise Planned Development District (PDD) classification to allow timely and predictable review and approval for flexibility within appropriate abandoned or underutilized areas | 1.2.3 | 2 | PZ, ED | GF, G
Strategy 1.2.4 - Identify sub-area planning and applicable zoning changes:
Consider stakeholder uses | 1.2.4 | 2 | PZ, ED | GF, G | In Process
Meet with representatives from Covenant and St Mary’s to coordinate their development plans that may include possible new/renovated housing developments | 1.2.4 | 2 | PZ, ED | GF, G, Other | In Process
Update the zoning ordinance to allow mixed-use building forms by-right in identified areas of concentrated development while preserving historical assets | 1.2.4 | 2 | PZ, ED | GF, G, Other | In Process
Work with legal counsel to develop restrictive overlay areas that would preserve historic assets desired by the neighborhood while providing flexibility for other mixed uses | 1.2.4 | 3 | PZ, ED | GF | In Process
Goal 2: Create viable and attractive community
Strategy 2.1.1 - Leverage our position in the Great Lakes Bay Region with existing economic cluster (Manufacturing and Healthcare)
Capitalize on the City’s partnership with Saginaw Future to meet regularly with industry leaders in the community and stay informed on plans for private development | 2.1.1 | 3 | PZ, ED, PS, DDA, RDC | GF, G, Other | On Going
Continue to utilize Redevelopment Ready Communities best practices to ensure a clear and timely development process | 2.1.1 | 3 | PZ, ED, PS, DDA, RDC | GF, G | On Going
Ensure zoning codes are written clearly to be easily understood by industry and development professionals | 2.1.1 | 3 | PZ, ED, PS, DDA, RDC | GF, G | In Process
When projects include difficult aspects, gather the development team to collaborate and create solutions to make the development happen | 2.1.1 | 3 | PZ, ED, PS, DDA, RDC | GF, G, Other | In Process
Key:
Timeframe - 1: Within a year, 2: 1 to 3 years, 3: More than 3 years, Ongoing: As available/Continuing project
Responsibility - CC: City Council, PZ: Planning & Zoning, ED: Economic Development Division, DDA: Downtown Development Authority, PS: Public Services, Parks: Technical Services, LB: Saginaw County Land Bank, BRA: Brownfield Redevelopment Authority, SHC: Saginaw Housing Commission, R: Riverfront Development Commission, MDOT - Michigan Department of Transportation
Funding - GF: General Fund, Grant: Grants, F: Area Foundations, Other: State and Federal Agencies
Tasks | Strategy | Timeframe | Responsibility | Funding | STATUS
Strategy 2.1.2 - Center on developing a diverse job base
Focus marketing efforts on companies that correlate with the existing industry-base in Saginaw while also encouraging innovative developments | 2.1.2 | Ongoing | PZ, ED, PS, DDA, RDC | GF, G, Other | On Going
Identify areas within the City with potential for new industry types | 2.1.2 | Ongoing | PZ, ED, PS, DDA, RDC | GF, G | In Process
Modify zoning codes to include flexible regulations to eliminate barriers to development for new industry types | 2.1.2 | 2 | PZ, ED, PS, DDA, RDC | GF, G | In Process
Strategy 2.1.3 - Create an entertainment district as a destination location
Collaborate with the Riverfront Development Commission to identify the boundaries for an entertainment district | 2.1.3 | 2 | PZ, ED, PS, DDA, RDC | GF, G, Other | In Process
Create an overlay zoning district that promotes walkability and the development of entertainment businesses, housing, public gathering spaces and other related features | 2.1.3 | 2 | PZ, ED, PS, DDA, RDC | GF, G, Other | In Process
Capitalize on the entertainment venues already existing in the city core | 2.1.3 | 2 | PZ, ED, PS, DDA, RDC | GF, G, Other | On Going
Focus on pedestrian oriented public spaces and developments | 2.1.3 | 2 | PZ, ED, PS, DDA, RDC | GF, G, Other | On Going
Strategy 2.1.4 - Market the City regionally as well as globally
Continue to showcase stories about the processes, individuals, organizations and businesses that make Saginaw a great a place to live, work and raise a family | 2.1.4 | 3 | PZ, ED, PS, DDA, RDC | GF, G, F, Other | On Going
Analyze available buildings and properties to determine the most viable for development | 2.1.4 | 2 | PZ, ED, PS, LB, DDA, RDC, BRA | GF, G, Other | On Going
Look for opportunities to improve and preserve Saginaw’s historic building stock in anticipation of redevelopment | 2.1.4 | Ongoing | PZ, ED, SHC | GF, G, Other | On Going
Regularly update the City’s priority redevelopment sites on MEDC’s website | 2.1.4 | Ongoing | PZ, ED, PS, LB, DDA, RDC, BRA | GF, G, Other | On Going
Capitalize on the City’s partnership with Saginaw Future to continue marketing development opportunities on Greatlakesbaysites.com, as well as, provide properties that meet specifications of businesses and developers looking to expand in or move to Saginaw | 2.1.4 | Ongoing | PZ, ED, PS, LB, DDA, RDC, BRA | GF, G, Other | On Going
Strategy 2.1.5 - Assemble and market vacant properties to attract new investment
Identify large vacant properties with potential for redevelopment | 2.1.5 | 1 | PZ, ED, PS, LB, DDA, RDC, BRA | GF, G, Other | In Process
Create language in the zoning ordinance that allows for a Planned Development District (PDD) to capitalize on the utilization of the property | 2.1.5 | 2 | PZ, ED, PS | GF, G, Other | In Process
Key:
Timeframe - 1: Within a year, 2: 1 to 3 years, 3: More than 3 years, Ongoing: As available/Continuing project
Responsibility - CC: City Council, PZ: Planning & Zoning, ED: Economic Development Division, DDA: Downtown Development Authority, PS: Public Services, Parks: Technical Services, LB: Saginaw County Land Bank, BRA: Brownfield Redevelopment Authority, SHC: Saginaw Housing Commission, R: Riverfront Development Commission, MDOT - Michigan Department of Transportation
Funding - GF: General Fund, Grant: Grants, F: Area Foundations, Other: State and Federal Agencies
Tasks | Strategy | Timeframe | Responsibility | Funding | STATUS
Strategy 2.1.6 - Encourage new mixed-use developments that include public access and enhance natural amenities |  |  |  |  | STATUS
Introduce ordinance changes that allow mixed-use buildings by- right in designated areas of concentrated development. Proposed changes to include: | 2.1.6 | 3 | PZ, ED, PS | GF, G, Other | In Process
Build-to lines | 2.1.6
Open storefronts | 2.1.6
Outdoor dining | 2.1.6
Minimum ground floor transparency | 2.1.6
Front-facing doorways | 2.1.6
Parking located in the rear of the building | 2.1.6
Strategy 2.2.1 - Create a parks management system that is sustainable
Ensure parks have a maintenance plan that is feasible and sustainable | 2.2.1 | Ongoing | PZ, ED, P, PS | GF, G, Other | On Going
Create a plan to naturalize certain recreation areas to help lower maintenance and cost | 2.2.1 | 3 | PZ, ED, P, PS | GF, G, Other | In Process
Continue partnerships with organizations and neighborhoods (including grants, user fees, volunteer contributions, private organizations, etc.) | 2.2.1 | Ongoing | PZ, ED, P, PS | GF, G, Other | On Going
Maintain the communication and coordinate with “adopt a park” groups to continue the success of the park maintenance and partnership | 2.2.1 | Ongoing | PZ, ED, P, PS | GF, G, Other | On Going
Preserve scenic views, improve safety, and stabilize the Riverfront | 2.2.1 | Ongoing | PZ, ED, P, PS, DDA, RDC | GF, G, Other | In Process
Strategy 2.2.2 - Provide safe, clean, and well-maintained parks and facilities
Evaluate the level of use and the users of neighborhood parks to determine what improvements should be made in the parks | 2.2.2 | 2 | PZ, ED, P, PS | GF, G, Other | In Process
Promote and provide diverse recreational opportunities to satisfy all age groups and levels of ability | 2.2.2 | Ongoing | PZ, ED, P, PS | GF, G, Other | On Going
Develop plans that address potential shifts in neighborhood parks | 2.2.2 | Ongoing | PZ, ED, P, PS | GF, G, Other | On Going
Incorporate Crime Prevention Through Environmental Design in parks and open spaces | 2.2.2 | 3 | PZ, ED, P, PS | GF, G, Other
Integrate a plan to repair parks on an annual basis | 2.2.2 | Ongoing | PZ, ED, P, PS | GF, G, Other | On Going
Explore adding new/additional amenities into the parks | 2.2.2 | 2 | PZ, ED, P, PS | GF, G, Other | In Process
Key:
Timeframe - 1: Within a year, 2: 1 to 3 years, 3: More than 3 years, Ongoing: As available/Continuing project
Responsibility - CC: City Council, PZ: Planning & Zoning, ED: Economic Development Division, DDA: Downtown Development Authority, PS: Public Services, Parks: Technical Services, LB: Saginaw County Land Bank, BRA: Brownfield Redevelopment Authority, SHC: Saginaw Housing Commission, R: Riverfront Development Commission, MDOT - Michigan Department of Transportation
Funding - GF: General Fund, Grant: Grants, F: Area Foundations, Other: State and Federal Agencies
Tasks | Strategy | Timeframe | Responsibility | Funding | STATUS
Strategy 2.2.3 - Develop a financial strategy to sustain and enhance City parks |  |  |  |  | STATUS
Consider/seek new partnerships that involve development and maintenance to the parks | 2.2.3 | Ongoing | PZ, ED, PS | GF, G, Other | On Going
Create, facilitate, or otherwise provide for coordinating of all parks open space and recreation stakeholders, organizations, and friend groups | 2.2.3 | Ongoing | PZ, ED, PS | GF, G, Other | On Going
Create a funding source for the parks and recreation in the City Budget | 2.2.3 | 2 | PZ, ED, PS | GF, G, Other
Recreate/encourage existing recreation programming through partnerships or City Budget | 2.2.3 | 2 | PZ, ED, PS | GF, G, Other
Partner with the County, Riverfront Commission, friend groups and neighborhood organizations to back the funding of projects | 2.2.3 | Ongoing | PZ, ED, PS | GF, G, Other | On Going
Explore options for new and expanded partnerships to provided additional recreational opportunities | 2.2.3 | Ongoing | PZ, ED, PS | GF, G, Other | On Going
Strategy 2.2.4 - Capitalize on the importance and function of community and regional parks
Carefully plan and budget for improvements to maintain the desirability and functionality of community and regional parks | 2.2.4 | Ongoing | PZ, ED, PS | GF, G, Other | On Going
Develop a capital improvement plan for all parks, account for routine replacement and maintenance costs and necessary improvements | 2.2.4 | Ongoing | PZ, ED, PS | GF, G, Other | On Going
Continue to build on the success and momentum of the Saginaw River | 2.2.4 | Ongoing | PZ, ED, PS, DDA, RDC | GF, G, Other | On Going
Support the Riverfront Commission in pursuit of their goals of improving the waterfront areas | 2.2.4 | Ongoing | PZ, ED, PS, DDA, RDC | GF, G, Other | On Going
Market and capitalize on the resources of the City to bring in additional park users to the City | 2.2.4 | Ongoing | PZ, ED, PS, DDA, RDC | GF, G, Other | On Going
Support efforts of the other local recreation groups such as GLBRT, DDA, and Saginaw Future for recreation improvements | 2.2.4 | Ongoing | PZ, ED, PS | GF, G, Other | On Going
If appropriate, acquire additional park land which supports high- quality natural resource access and fits within the existing park system | 2.2.4 | Ongoing | PZ, ED, PS | GF, G, Other | On Going
Key:
Timeframe - 1: Within a year, 2: 1 to 3 years, 3: More than 3 years, Ongoing: As available/Continuing project
Responsibility - CC: City Council, PZ: Planning & Zoning, ED: Economic Development Division, DDA: Downtown Development Authority, PS: Public Services, Parks: Technical Services, LB: Saginaw County Land Bank, BRA: Brownfield Redevelopment Authority, SHC: Saginaw Housing Commission, R: Riverfront Development Commission, MDOT - Michigan Department of Transportation
Funding - GF: General Fund, Grant: Grants, F: Area Foundations, Other: State and Federal Agencies
Tasks | Strategy | Timeframe | Responsibility | Funding | STATUS
Strategy 2.2.5 - Provide safe non-motorized travel network linking various parks to the central park area |  |  |  |  | STATUS
Work to strengthen connections to existing parks and the riverfront from neighborhoods through a network of sidewalks and non-motorized pathways | 2.2.5 | 2 | PZ, ED, PS | GF, G, Other | In Process
Create a more connected and safe system | 2.2.5 | 2 | PZ, ED, PS | GF, G, Other | In Process
Continue the linkage of the bikeways and existing Riverwalk | 2.2.5 | 2 | PZ, ED, PS, DDA, RDC | GF, G, Other | In Process
Explore future connections to other non-motorized trails within the County | 2.2.5 | 2 | PZ, ED, PS | GF, G, Other | In Process
Support non-motorized bike lanes and complete street projects and connectivity | 2.2.5 | 3 | PZ, ED, PS | GF, G, Other | In Process
Goal 3: Provide adequate and cost-effective public services
Strategy 3.1.1 - Provide strategic enhancements to the City’s Gateways
Identify and prioritize main thoroughfares for gateway enhancements | 3.1.1 | 2 | PZ, ED, PS | GF, G, F, Other | In Process
Create identification and wayfinding signage highlighting various City attractions | 3.1.1 | 2 | PZ, ED, PS, DDA, RDC | GF, G, F, Other
Strategy 3.1.2 - Provide and pursue multi-modal transportation alternatives to improve connectivity
Implement the City of Saginaw Complete Street Ordinance on all newly constructed roads | 3.1.2 | Ongoing | PZ, ED, PS | GF, G, Other | On Going
Continue to identify funding sources for non-motorized pathways connecting neighborhoods with each other and the Central Core | 3.1.2 | Ongoing | PZ, ED, PS | GF, G, Other | On Going
Support STARS in their efforts to expand public transit services | 3.1.2 | Ongoing | PZ, ED, PS | GF, G, Other | On Going
Strategy 3.1.3 - Incorporate Complete Streets principles and practices to create a transportation network
Further refine non-motorized pathways routes and develop a plan to implement | 3.1.3 | 3 | PZ, ED, P, PS | GF, G, Other | In Process
Prioritize connectivity between neighborhoods and traffic generators such as schools, grocery stores, recreation amenities, commercial areas and medical facilities | 3.1.3 | 2 | PZ, ED, PS | GF, G, Other | In Process
Develop a traffic calming plan that can be utilized to slow traveling speeds | 3.1.3 | 3 | PZ, ED, PS | GF, G, Other | In Process
Key:
Timeframe - 1: Within a year, 2: 1 to 3 years, 3: More than 3 years, Ongoing: As available/Continuing project
Responsibility - CC: City Council, PZ: Planning & Zoning, ED: Economic Development Division, DDA: Downtown Development Authority, PS: Public Services, Parks: Technical Services, LB: Saginaw County Land Bank, BRA: Brownfield Redevelopment Authority, SHC: Saginaw Housing Commission, R: Riverfront Development Commission, MDOT - Michigan Department of Transportation
Funding - GF: General Fund, Grant: Grants, F: Area Foundations, Other: State and Federal Agencies
Tasks | Strategy | Timeframe | Responsibility | Funding | STATUS
Strategy 3.2.1 - Capitalize on the City-wide and regional importance of the Saginaw River as an asset for economic development |  |  |  |  | STATUS
Budget for the continuation of trails connections within the City of Saginaw Riverfront area | 3.2.1 | 1 | PZ, ED, PS, DDA, RDC | GF, G, Other | In Process
Saginaw River Loop | 3.2.1
Wickes Park | 3.2.1 |  |  |  | In Process
Ojibway Island | 3.2.1 |  |  |  | In Process
Green Point Pathway | 3.2.1
Iron Belle Trail | 3.2.1 |  |  |  | In Process
Develop plans to make connections to County-wide non- motorized routes | 3.2.1 | 3 | PZ, ED, PS, DDA, RDC | GF, G, Other | In Process
Harger Line Trail | 3.2.1
Saginaw Valley Rail Trail | 3.2.1 |  |  |  | In Process
Iron Belle to Carrollton | 3.2.1 |  |  |  | In Process
Kochville Township Pathway | 3.2.1
Saginaw Township Pathway | 3.2.1 |  |  |  | In Process
Strategy 3.2.2 - Provide functional and attractive public places
Identify areas within the Downtown, Old Town and key corridor nodes, such as Court Street, to create quality pedestrian- oriented projects/activities | 3.2.2 | 2 | PZ, ED, DDA, RDC, PS | GF, G, Other | In Process
Implement strategic placemaking to create projects/activities that are uniquely attractive to talented workers so that they want to work and live here | 3.2.2 | 2 | PZ, ED, DDA, RDC, PS | GF, G, Other | In Process
Strategy 3.2.3 - Utilize Redevelopment Ready Communities best practices to create a strong vision for redevelopment in Saginaw.
Work toward maintaining Redevelopment Ready Community certification status | 3.2.3 | Ongoing | PZ, ED, | GF, G, Other | On Going
Commit to improving development readiness by undergo continuous assessments and working locally to integrate best practices | 3.2.3 | Ongoing | PZ, ED, | GF, G, Other | On Going
Strategy 3.3.1 - Utilize the County's Hazard Mitigation Plan to protect the residents, visitors, and property within the City.
Identify projects from the Hazard Mitigation Plan to be initiated that might mitigate damages from local hazards that negatively impact the City. | 3.3.1 | 2 | PS | GF, G, Other | In Process
Seek funding to complete the projects identified above | 3.3.1 | 2 | PS | GF, G, Other | In Process
Strategy 3.4.1 - Update the asset management strategy to address all public infrastructure needs.
Review existing asset management strategy and identify deficiencies or gaps. | 3.4.1 | 2 | PS |  | In Process
Participate in State of Michigan Asset Management Readiness Program. | 3.4.1 | 2 | PS
Put in place a governance structure to ensure vision and objectives are acted upon, then develop policies and objectives to connect the vision to actions. | 3.4.1 | Ongoing | PS |  | On Going
Key:
Timeframe - 1: Within a year, 2: 1 to 3 years, 3: More than 3 years, Ongoing: As available/Continuing project
Responsibility - CC: City Council, PZ: Planning & Zoning, ED: Economic Development Division, DDA: Downtown Development Authority, PS: Public Services, Parks: Technical Services, LB: Saginaw County Land Bank, BRA: Brownfield Redevelopment Authority, SHC: Saginaw Housing Commission, R: Riverfront Development Commission, MDOT - Michigan Department of Transportation
Funding - GF: General Fund, Grant: Grants, F: Area Foundations, Other: State and Federal Agencies